## Overview
Dona Dom — Phase 1 Roadmap
10 weeks to a live pilot · August 24 – October 30, 2026
WHAT PHASE 1 DELIVERS
Tenant AI Assistant | Repairs, Handled | Office Control Panel
Tenants chat and get instant answers drawn from their own lease — with the exact source shown. | A reported fault becomes a booked technician visit — guided help first, booking and updates automatic. | One queue for the team: full visibility, clear priorities, and human approval where it matters.
Built on foundations designed for change — every part can be extended or redesigned later without starting over.
KEY MILESTONES
Aug 28 | First version live online
Sep 25 | First real tenant conversation
Oct 16 | Full repair loop — no staff needed
Oct 30 | Pilot launch with real tenants
SYSTEM CAPABILITIES ONLINE, WEEK BY WEEK
Week | Capabilities live (cumulative)
W1 | 1
W2 | 2
W3 | 2
W4 | 3
W5 | 4
W6 | 5
W7 | 5
W8 | 6
W9 | 7
W10 | 8
Counts the 8 capability groups on the Gantt tab as each goes live (weeks 1-10). Source: docs/PHASE1-ROADMAP.md.
Assumed start: Monday August 24, 2026 (shift all dates together if the start moves). Full detailed plan: docs/PHASE1-ROADMAP.md.

## Gantt
Phase 1 — Weekly Plan
Each bar = when that part of the system is built and switched on.
| Week 1 Aug 24 | Week 2 Aug 31 | Week 3 Sep 07 | Week 4 Sep 14 | Week 5 Sep 21 | Week 6 Sep 28 | Week 7 Oct 05 | Week 8 Oct 12 | Week 9 Oct 19 | Week 10 Oct 26
System online + release pipeline | ◆
Buildings, tenants & staff access
AI reads the leases
Tenant chat goes live |  |  |  |  | ◆
Fault reports & office queue
Technician scheduling | [7 empty] | ◆
Reliability & security
Pilot launch (real tenants) | [9 empty] | ◆
WhatsApp approval (external, in parallel)
Real data onboarding (leases & tenants)
Legend
|  | Build weeks |  | Make it bulletproof |  | Launch |  | Runs in the background
| ◆ | Milestone
Milestones
Aug 28 | First version live online
Sep 25 | First real tenant conversation
Oct 16 | Full repair loop — no staff needed
Oct 30 | Pilot launch with real tenants

## Milestones
Milestones — what you'll actually see
Date | Milestone | What it looks like
Aug 28 | First version live | The system is on the internet with automatic, safe updates — every improvement from here ships within a day.
Sep 25 | First real tenant conversation | A tenant verifies with a code to their phone and asks about their lease — the answer quotes the exact contract clause.
Oct 16 | Repair loop, hands-free | A fault is reported in chat, quick self-fixes are tried first, the tenant approves the co-payment, a technician accepts and is booked — nobody at the office lifted a finger.
Oct 30 | Pilot launch | Real tenants of the pilot building are invited in. The office watches everything from the control panel and can step in at any moment.
What "live" means at the end of week 10
✓ | Real tenants get lease answers with the source shown — on the live system
✓ | A real fault becomes a booked technician visit, start to finish, automatically
✓ | The office has one clear queue, roles & permissions, and a full activity log
✓ | Any feature can be switched off instantly if something misbehaves
✓ | Tenant privacy is absolute — one tenant can never see another's information
✓ | Updates ship safely in minutes, and can be rolled back in one step

## Scope
Scope at a glance
IN THIS PHASE | COMING LATER
• Tenant chat on the website (Hebrew) | • WhatsApp as a chat channel (approval already in progress)
• Phone-code identity check before any personal answer | • More languages (Russian, French, Arabic)
• Lease answers with the exact source shown | • Account & invoice questions (finance system link)
• Fault reports with guided self-help first | • Lease renewal reminders and offers
• Co-payment approval recorded in chat | • Move-in guidance & utility transfers
• Automatic technician offers & booking | • Preventive maintenance (fix before it breaks)
• Office control panel: queue, roles, full activity log | • Supplier work portal
• Instant, safe updates with one-step rollback | • Voice calls
Payments are never handled by the system — by design. It informs and records approvals; people and existing systems move money.